## Brief
Workforce Management System Implementation - Business Analyst portfolio project
Self-directed project modelled on a BA role supporting a WFM / Field Service / time & attendance rollout. All data is synthetic.
Scenario | Fictional environmental services company moving ~2,300 staff in Australia and New Zealand from paper timesheets and legacy HR onto a new Workforce Management and Field Service system.
Your role | Business Analyst reporting to the Head of Transformation: requirements, process mapping, configuration, data migration, UAT, training and go-live support.
How to read it | Start at Dashboard. Then Requirements -> Process_Map -> Config -> Validation -> Recon -> UAT -> GoLive_Training. Resume_Uplift maps each gap to a bullet.
Key finding | Migration accuracy is well below go-live standard; defects trace back to source data issues and load mappings. See Validation and Recon.
Skills demonstrated | Requirements gathering, process mapping, system configuration, data migration, validation, reconciliation, INDEX/MATCH, pivot-style reporting, UAT, training materials, stakeholder engagement.
Assumptions | All people, award codes, rates and UAT results are fictional/simulated. Blue font = editable inputs. Replace or extend with your own data.
Stretch tasks | 1) Build a real PivotTable on Recon. 2) Add a Python/pandas script that reproduces Recon. 3) Draw the process map in Lucidchart. 4) Write a one-page go/no-go memo from the Dashboard numbers.

## Dashboard
Dashboard - migration health, test results and requirements coverage
All figures are live formulas.
Data migration |  | Region | Legacy | Match | Mismatch | Missing | Accuracy
Legacy records | 62 | NSW | 14 | 9 | 4 | 1 | 64.29%
Records in WFM | 59 | VIC | 17 | 12 | 2 | 3 | 70.59%
Match | 48 | QLD | 16 | 14 | 2 | 0 | 87.5%
Field mismatches | 10 | NZ | 15 | 13 | 2 | 0 | 86.67%
Missing in WFM | 4 | Total | 62 | 48 | 10 | 4 | 77.42%
Orphans in WFM (not in legacy) | 3
Migration accuracy (Match / Legacy) | 77.42% | Note: pivot-style table via COUNTIFS. Extension task: build a real PivotTable on Recon (Insert > PivotTable).
Pre-migration data quality
Records failing validation | 12
Duplicate IDs | 4
Missing/invalid emails | 3
Invalid award codes | 2
Rates out of range | 2
Invalid start dates | 1
UAT
Total test cases | 17
Pass | 11
Fail | 3
Blocked | 1
Not Run | 2
Pass rate | 64.71%
Requirements
Total requirements | 15
Must-haves | 10
Coverage gaps | 0

## Requirements
Requirements - traceability matrix (RTM)
Priority = MoSCoW. 'UAT cases' and 'Coverage' are formulas against the UAT sheet.
ID | Requirement | Type | Stakeholder | Priority | Process area | UAT cases | Coverage | Status
R01 | Employees clock in/out on mobile with GPS location capture | Functional | Field Ops Manager | Must | Time & attendance | 2 | Covered | Approved
R02 | Rosters built per depot with skills/qualification matching | Functional | Depot Team Leaders | Must | Rostering | 1 | Covered | Approved
R03 | System applies overtime and penalty rates per award code | Functional | Payroll Manager | Must | Pay rules | 2 | Covered | Approved
R04 | Leave requests submitted and approved in-system | Functional | HR | Should | Leave | 1 | Covered | Approved
R05 | Field jobs scheduled and dispatched to nearest qualified crew | Functional | Field Ops Manager | Must | Field service | 2 | Covered | Approved
R06 | Employee master data migrated from legacy HR with zero critical defects | Data | Head of Transformation | Must | Data migration | 2 | Covered | Approved
R07 | Team leaders approve timesheets before payroll cut-off | Functional | Payroll Manager | Must | Time & attendance | 1 | Covered | Approved
R08 | Approved hours exported to payroll in agreed file format | Integration | Payroll Manager | Must | Integration | 1 | Covered | Approved
R09 | NZ employees follow separate public holiday and pay rules | Functional | NZ Operations Lead | Must | Pay rules | 1 | Covered | Approved
R10 | Weekly labour cost report by region and role | Reporting | Finance | Should | Reporting | 1 | Covered | Approved
R11 | Role-based access (employee, team leader, admin) | Non-functional | IT Security | Must | Security | 1 | Covered | Approved
R12 | Audit trail on every timesheet edit | Non-functional | Internal Audit | Should | Compliance | 1 | Covered | Approved
R13 | Roster publish completes in under 60 seconds for 2,300 employees | Non-functional | IT Architect | Should | Performance | 1 | Covered | Approved
R14 | Role-specific user guides and quick-reference cards | Training | Training Lead | Must | Training | 0 | Via training plan | Approved
R15 | Four weeks of hypercare support post go-live | Training | Head of Transformation | Should | Adoption | 0 | Via training plan | Approved

## Process_Map
Process_Map - Timesheet to pay: current vs future state
Text-based process map (swap in a Visio/Lucidchart diagram if you want to extend it).
Step | Current state (as-is) | Pain point | Future state (to-be) | System | Owner | Req ID
1 | Employee writes hours on paper timesheet | Illegible, late, lost sheets | Employee clocks in/out on mobile app | WFM mobile | Employee | R01
2 | Team leader collects sheets and emails to admin | 2-3 day delay | Hours flow to team leader approval queue automatically | WFM | System | R07
3 | Admin re-keys hours into spreadsheet | Re-keying errors, ~5% rework | No re-keying: single source of truth | WFM | System | R07
4 | Payroll applies overtime rules by hand | Inconsistent rule application | Award rules applied by configured rule engine | WFM config | Payroll | R03
5 | Exceptions chased by phone | No audit trail | Exception dashboard with audit trail on edits | WFM | Team Leader | R12
6 | Payroll manager prepares upload file | Manual, error-prone | Automated export in payroll file format | Integration | Payroll | R08
7 | Finance builds labour cost report in Excel | Report 5+ days after period end | Weekly report by region and role | WFM reporting | Finance | R10

## Config
Config - system configuration baseline
Blue = editable input. All award codes and rates are FICTIONAL (not a real industrial award).
Award code | Description | Base rate ($/hr) | OT multiplier | Weekend multiplier | Min engagement (hrs) | Setting | Value
FS-L1 | Field Services Level 1 (Cleaner) | 32 | 1.5 | 1.5 | 3 | Min valid hourly rate ($) | 25
FS-L2 | Field Services Level 2 (Driver/Helper) | 36 | 1.5 | 1.5 | 3 | Max valid hourly rate ($) | 70
FS-L3 | Field Services Level 3 (Technician) | 41 | 1.5 | 1.5 | 3 | Ordinary hours cap per shift | 7.6
TL-L4 | Team Leader Level 4 | 48 | 1.5 | 1.75 | 4 | Data extract date | 2026-10-01
ADM-L2 | Depot Admin Level 2 | 34 | 2 | 1.5 | 4
Worked example: overtime pay rule (use to test configuration logic)
Award code | FS-L2
Hours worked in shift | 10.5
Ordinary hours | 7.6
Overtime hours | 2.9
Base rate | 36
OT multiplier | 1.5
Gross pay ($) | 430.2
Assumption: 7.6 ordinary hours/shift and OT multipliers are illustrative, set to mimic typical award logic.

## Legacy_Employees
Legacy_Employees - source extract (synthetic)
Legacy HR/payroll extract. Contains deliberately seeded data quality defects for the validation exercise.
Employee ID | Name | Region | Role | Award code | Start date | Hourly rate ($) | Email
E1001 | Oscar Hall | VIC | Driver | FS-L2 | 2015-07-17 | 36 | oscar.hall@example.com
E1002 | Ruby Green | NSW | Cleaner | FS-L1 | 2015-08-26 | 32 | ruby.green@example.com
E1003 | Olivia Patel | VIC | Team Leader | TL-L4 | 2019-11-12 | 48 | olivia.patel@example.com
E1004 | Noah Scott | VIC | Driver | FS-L2 | 2019-10-05 | 36 | noah.scott@example.com
E1005 | Chloe Hall | NSW | Cleaner | FS-L1 | 2022-01-13 | 32
E1006 | Max Green | NSW | Field Technician | FS-L3 | 2019-06-13 | 41 | max.green@example.com
E1007 | Olivia Scott | VIC | Cleaner | FS-L1 | 2016-06-29 | 32 | olivia.scott@example.com
E1008 | Ella Brown | VIC | Driver | FS-L2 | 2021-05-27 | 36 | ella.brown@example.com
E1009 | Ava Green | VIC | Driver | FS-L2 | 2021-05-28 | 36 | ava.green@example.com
E1010 | Ava Scott | QLD | Field Technician | FS-L9 | 2022-12-26 | 41 | ava.scott@example.com
E1011 | Sophie Singh | NSW | Cleaner | FS-L1 | 2020-07-26 | 32 | sophie.singh@example.com
E1012 | Tane Anderson | NZ | Field Technician | FS-L3 | 2020-03-22 | 41 | tane.anderson@example.com
E1013 | Ruby Ng | NZ | Field Technician | FS-L3 | 2017-10-14 | 0 | ruby.ng@example.com
E1014 | Noah Green | VIC | Field Technician | FS-L3 | 2018-05-14 | 41 | noah.green@example.com
E1015 | Aroha Young | QLD | Driver | FS-L2 | 2018-03-25 | 36 | aroha.young@example.com
E1016 | Ava Wright | NSW | Field Technician | FS-L3 | 2019-09-09 | 41 | ava.wright@example.com
E1017 | Ethan King | QLD | Cleaner | FS-L1 | 2019-09-24 | 32 | ethan.king@example.com
E1018 | Tane Scott | NSW | Cleaner | FS-L1 | 2021-06-05 | 32
E1019 | Jack Ward | QLD | Field Technician | FS-L3 | 2018-12-05 | 41 | jack.ward@example.com
E1020 | Noah Parker | NZ | Field Technician | FS-L3 | 2016-01-19 | 41 | noah.parker@example.com
E1021 | Wiremu Lee | NZ | Depot Admin | ADM-L2 | 2015-09-24 | 34 | wiremu.lee@example.com
E1022 | Arjun Green | QLD | Cleaner | FS-L1 | 2022-08-22 | 32 | arjun.green@example.com
E1023 | Wiremu Harris | QLD | Field Technician | FS-L3 | 2022-07-01 | 41 | wiremu.harris@example.com
E1024 | Ruby Taylor | NZ | Driver | FS-L2 | 2021-11-07 | 36 | ruby.taylor@example.com
E1025 | Lucas Turner | NSW | Cleaner | FS-L1 | 2018-03-23 | 32 | lucas.turner@example.com
E1026 | Oscar Harris | VIC | Cleaner | FS-L1 | 2020-07-26 | 32 | oscar.harris@example.com
E1027 | Oscar Scott | NZ | Cleaner | FS-L1 | 2018-02-12 | 32 | oscar.scott@example.com
E1028 | Hannah Scott | NZ | Team Leader | TL-L4 | 2027-03-14 | 48 | hannah.scott@example.com
E1029 | Priya Harris | QLD | Field Technician | FS-L3 | 2017-08-03 | 41 | priya.harris@example.com
E1030 | Ethan Kelly | VIC | Cleaner | FS-L1 | 2022-05-21 | 32 | ethan.kelly@example.com
E1031 | Sam Green | NZ | Cleaner | FS-L1 | 2017-01-16 | 32 | sam.green@example.com
E1032 | Ethan Clarke | NSW | Cleaner | FS-L1 | 2020-12-29 | 32 | ethan.clarke@example.com
E1033 | Ethan Ward | QLD | Driver | FS-L2 | 2020-10-12 | 36 | ethan.ward@example.com
E1034 | Leo Murphy | NSW | Depot Admin | ADM-L2 | 2023-09-30 | 34
E1035 | Oscar Harris | NZ | Depot Admin | ADM-L2 | 2019-06-03 | 34 | oscar.harris@example.com
E1036 | Olivia Singh | NZ | Cleaner | FS-L1 | 2015-10-03 | 32 | olivia.singh@example.com
E1037 | Mia Brown | NZ | Depot Admin | ADM-L2 | 2018-10-24 | 34 | mia.brown@example.com
E1038 | Liam Green | NSW | Field Technician | FS-L3 | 2016-09-11 | 41 | liam.green@example.com
E1039 | Sophie Nguyen | QLD | Driver | FS-L2 | 2015-10-16 | 36 | sophie.nguyen@example.com
E1040 | Ethan Hall | NZ | Team Leader | TL-L4 | 2017-10-30 | 48 | ethan.hall@example.com
E1041 | Grace Brown | QLD | Depot Admin | ADM-L2 | 2016-04-17 | 34 | grace.brown@example.com
E1042 | Grace King | NZ | Team Leader | TL4 | 2018-07-01 | 48 | grace.king@example.com
E1043 | Aroha Anderson | NSW | Cleaner | FS-L1 | 2023-04-21 | 32 | aroha.anderson@example.com
E1044 | Henry Nguyen | VIC | Cleaner | FS-L1 | 2017-04-20 | 32 | henry.nguyen@example.com
E1045 | Ethan Ward | QLD | Depot Admin | ADM-L2 | 2021-02-02 | 34 | ethan.ward@example.com
E1046 | Arjun Murphy | QLD | Team Leader | TL-L4 | 2016-01-08 | 48 | arjun.murphy@example.com
E1047 | Henry Thomas | QLD | Field Technician | FS-L3 | 2016-11-15 | 41 | henry.thomas@example.com
E1048 | Ella Scott | VIC | Driver | FS-L2 | 2023-09-27 | 36 | ella.scott@example.com
E1049 | Sophie Reid | VIC | Driver | FS-L2 | 2023-11-04 | 36 | sophie.reid@example.com
E1050 | Mereana Kelly | VIC | Depot Admin | ADM-L2 | 2024-03-05 | 34 | mereana.kelly@example.com
E1051 | Lucas Wright | VIC | Driver | FS-L2 | 2020-07-11 | 540 | lucas.wright@example.com
E1052 | Liam Reid | NSW | Driver | FS-L2 | 2018-02-18 | 36 | liam.reid@example.com
E1053 | Wiremu Baker | VIC | Driver | FS-L2 | 2018-11-11 | 36 | wiremu.baker@example.com
E1054 | Ruby Patel | QLD | Driver | FS-L2 | 2017-06-22 | 36 | ruby.patel@example.com
E1055 | Lucas Anderson | NZ | Cleaner | FS-L1 | 2017-04-17 | 32 | lucas.anderson@example.com
E1056 | Grace Hall | NSW | Driver | FS-L2 | 2018-11-10 | 36 | grace.hall@example.com
E1057 | Sam Lee | NSW | Field Technician | FS-L3 | 2016-05-06 | 41 | sam.lee@example.com
E1058 | Grace Taylor | VIC | Team Leader | TL-L4 | 2019-11-13 | 48 | grace.taylor@example.com
E1059 | Noah Reid | QLD | Field Technician | FS-L3 | 2023-02-04 | 41 | noah.reid@example.com
E1060 | Aroha Patel | NZ | Driver | FS-L2 | 2023-02-16 | 36 | aroha.patel@example.com
E1007 | Olivia Scott | VIC | Cleaner | FS-L1 | 2016-06-29 | 32 | olivia.scott@example.com
E1023 | Wiremu Harris | QLD | Field Technician | FS-L3 | 2022-07-01 | 41 | wiremu.harris@example.com

## WFM_Import
WFM_Import - what actually landed in the new system (synthetic)
Post-load extract from the new Workforce Management system, with migration defects for reconciliation.
Employee ID | Name | Region | Role | Award code | Start date | Hourly rate ($) | Email | Orphan check (in WFM, not in legacy?)
E1001 | Oscar Hall | VIC | Driver | FS-L2 | 2015-07-17 | 36 | oscar.hall@example.com | OK
E1002 | Ruby Green | NSW | Cleaner | FS-L1 | 2015-08-26 | 32 | ruby.green@example.com | OK
E1004 | Noah Scott | VIC | Driver | FS-L2 | 2019-10-05 | 36 | noah.scott@example.com | OK
E1005 | Chloe Hall | NSW | Cleaner | FS-L1 | 2022-01-13 | 32 |  | OK
E1006 | Max Green | NSW | Field Technician | FS-L3 | 2019-06-13 | 45.1 | max.green@example.com | OK
E1007 | Olivia Scott | VIC | Cleaner | FS-L1 | 2016-06-29 | 32 | olivia.scott@example.com | OK
E1008 | Ella Brown | VIC | Driver | FS-L2 | 2021-05-27 | 36 | ella.brown@example.com | OK
E1009 | Ava Green | VIC | Driver | FS-L1 | 2021-05-28 | 36 | ava.green@example.com | OK
E1010 | Ava Scott | QLD | Field Technician | FS-L9 | 2022-12-26 | 41 | ava.scott@example.com | OK
E1011 | Sophie Singh | NSW | Cleaner | FS-L1 | 2020-07-26 | 32 | sophie.singh@example.com | OK
E1012 | Tane Anderson | NZ | Field Technician | FS-L3 | 2020-03-22 | 45.1 | tane.anderson@example.com | OK
E1013 | Ruby Ng | NZ | Field Technician | FS-L3 | 2017-10-14 | 0 | ruby.ng@example.com | OK
E1014 | Noah Green | VIC | Field Technician | FS-L3 | 2018-05-14 | 41 | noah.green@example.com | OK
E1015 | Aroha Young | QLD | Driver | FS-L2 | 2018-03-25 | 36 | aroha.young@example.com | OK
E1017 | Ethan King | QLD | Cleaner | FS-L1 | 2019-09-24 | 32 | ethan.king@example.com | OK
E1018 | Tane Scott | NSW | Cleaner | FS-L1 | 2021-06-05 | 32 |  | OK
E1019 | Jack Ward | QLD | Field Technician | FS-L3 | 2018-12-05 | 41 | jack.ward@example.com | OK
E1020 | Noah Parker | NZ | Field Technician | FS-L2 | 2016-01-19 | 41 | noah.parker@example.com | OK
E1021 | Wiremu Lee | NZ | Depot Admin | ADM-L2 | 2015-09-24 | 34 | wiremu.lee@example.com | OK
E1022 | Arjun Green | VIC | Cleaner | FS-L1 | 2022-08-22 | 32 | arjun.green@example.com | OK
E1023 | Wiremu Harris | QLD | Field Technician | FS-L3 | 2022-07-01 | 41 | wiremu.harris@example.com | OK
E1024 | Ruby Taylor | NZ | Driver | FS-L2 | 2021-11-07 | 36 | ruby.taylor@example.com | OK
E1025 | Lucas Turner | NSW | Cleaner | FS-L1 | 2018-03-23 | 35.2 | lucas.turner@example.com | OK
E1026 | Oscar Harris | VIC | Cleaner | FS-L1 | 2020-07-26 | 32 | oscar.harris@example.com | OK
E1027 | Oscar Scott | NZ | Cleaner | FS-L1 | 2018-02-12 | 32 | oscar.scott@example.com | OK
E1028 | Hannah Scott | NZ | Team Leader | TL-L4 | 2027-03-14 | 48 | hannah.scott@example.com | OK
E1029 | Priya Harris | QLD | Field Technician | FS-L3 | 2017-08-03 | 41 | priya.harris@example.com | OK
E1031 | Sam Green | NZ | Cleaner | FS-L1 | 2017-01-16 | 32 | sam.green@example.com | OK
E1032 | Ethan Clarke | NSW | Cleaner | FS-L1 | 2020-12-29 | 32 | ethan.clarke@example.com | OK
E1033 | Ethan Ward | QLD | Driver | FS-L2 | 2020-10-12 | 36 | ethan.ward@example.com | OK
E1034 | Leo Murphy | NSW | Depot Admin | ADM-L2 | 2023-09-30 | 34 |  | OK
E1035 | Oscar Harris | NZ | Depot Admin | ADM-L2 | 2019-06-03 | 34 | oscar.harris@example.com | OK
E1036 | Olivia Singh | NZ | Cleaner | FS-L1 | 2015-10-03 | 32 | olivia.singh@example.com | OK
E1037 | Mia Brown | NZ | Depot Admin | ADM-L2 | 2018-10-24 | 34 | mia.brown@example.com | OK
E1038 | Liam Green | NSW | Field Technician | FS-L3 | 2016-09-11 | 45.1 | liam.green@example.com | OK
E1039 | Sophie Nguyen | QLD | Driver | FS-L2 | 2015-10-16 | 36 | sophie.nguyen@example.com | OK
E1040 | Ethan Hall | NZ | Team Leader | TL-L4 | 2017-10-30 | 48 | ethan.hall@example.com | OK
E1041 | Grace Brown | QLD | Depot Admin | ADM-L2 | 2016-04-17 | 34 | grace.brown@example.com | OK
E1042 | Grace King | NZ | Team Leader | TL4 | 2018-07-01 | 48 | grace.king@example.com | OK
E1043 | Aroha Anderson | NSW | Cleaner | FS-L1 | 2023-04-21 | 32 | aroha.anderson@example.com | OK
E1044 | Henry Nguyen | VIC | Cleaner | FS-L1 | 2017-04-20 | 32 | henry.nguyen@example.com | OK
E1045 | Ethan Ward | QLD | Depot Admin | FS-L2 | 2021-02-02 | 34 | ethan.ward@example.com | OK
E1046 | Arjun Murphy | QLD | Team Leader | TL-L4 | 2016-01-08 | 48 | arjun.murphy@example.com | OK
E1047 | Henry Thomas | QLD | Field Technician | FS-L3 | 2016-11-15 | 41 | henry.thomas@example.com | OK
E1048 | Ella Scott | VIC | Driver | FS-L2 | 2023-09-27 | 36 | ella.scott@example.com | OK
E1050 | Mereana Kelly | VIC | Depot Admin | ADM-L2 | 2024-03-05 | 34 | mereana.kelly@example.com | OK
E1051 | Lucas Wright | VIC | Driver | FS-L2 | 2020-07-11 | 540 | lucas.wright@example.com | OK
E1052 | Liam Reid | NSW | Driver | FS-L2 | 2018-02-18 | 36 | liam.reid@example.com | OK
E1053 | Wiremu Baker | VIC | Driver | FS-L2 | 2018-11-11 | 39.6 | wiremu.baker@example.com | OK
E1054 | Ruby Patel | QLD | Driver | FS-L2 | 2017-06-22 | 36 | ruby.patel@example.com | OK
E1055 | Lucas Anderson | NZ | Cleaner | FS-L1 | 2017-04-17 | 32 | lucas.anderson@example.com | OK
E1056 | Grace Hall | VIC | Driver | FS-L2 | 2018-11-10 | 36 | grace.hall@example.com | OK
E1057 | Sam Lee | NSW | Field Technician | FS-L3 | 2016-05-06 | 41 | sam.lee@example.com | OK
E1058 | Grace Taylor | VIC | Team Leader | TL-L4 | 2019-11-13 | 48 | grace.taylor@example.com | OK
E1059 | Noah Reid | QLD | Field Technician | FS-L3 | 2023-02-04 | 41 | noah.reid@example.com | OK
E1060 | Aroha Patel | NZ | Driver | FS-L2 | 2023-02-16 | 36 | aroha.patel@example.com | OK
E2001 | Mia Taylor | VIC | Cleaner | FS-L1 | 2025-06-01 | 32 | mia.taylor | Orphan
E2002 | Liam Wilson | NZ | Cleaner | FS-L1 | 2025-06-01 | 32 | liam.wilson | Orphan
E2003 | Mereana Hall | VIC | Cleaner | FS-L1 | 2025-06-01 | 32 | mereana.hall | Orphan

## Validation
Validation - pre-migration data quality rules
Each rule is a formula against Legacy_Employees; thresholds come from Config. Fix source data BEFORE loading.
Employee ID | Duplicate ID | Email present/valid | Award code valid | Rate in range | Start date valid | Overall
E1001 | OK | OK | OK | OK | OK | Pass
E1002 | OK | OK | OK | OK | OK | Pass
E1003 | OK | OK | OK | OK | OK | Pass
E1004 | OK | OK | OK | OK | OK | Pass
E1005 | OK | Missing/invalid | OK | OK | OK | Fail
E1006 | OK | OK | OK | OK | OK | Pass
E1007 | Duplicate | OK | OK | OK | OK | Fail
E1008 | OK | OK | OK | OK | OK | Pass
E1009 | OK | OK | OK | OK | OK | Pass
E1010 | OK | OK | Invalid code | OK | OK | Fail
E1011 | OK | OK | OK | OK | OK | Pass
E1012 | OK | OK | OK | OK | OK | Pass
E1013 | OK | OK | OK | Out of range | OK | Fail
E1014 | OK | OK | OK | OK | OK | Pass
E1015 | OK | OK | OK | OK | OK | Pass
E1016 | OK | OK | OK | OK | OK | Pass
E1017 | OK | OK | OK | OK | OK | Pass
E1018 | OK | Missing/invalid | OK | OK | OK | Fail
E1019 | OK | OK | OK | OK | OK | Pass
E1020 | OK | OK | OK | OK | OK | Pass
E1021 | OK | OK | OK | OK | OK | Pass
E1022 | OK | OK | OK | OK | OK | Pass
E1023 | Duplicate | OK | OK | OK | OK | Fail
E1024 | OK | OK | OK | OK | OK | Pass
E1025 | OK | OK | OK | OK | OK | Pass
E1026 | OK | OK | OK | OK | OK | Pass
E1027 | OK | OK | OK | OK | OK | Pass
E1028 | OK | OK | OK | OK | Check date | Fail
E1029 | OK | OK | OK | OK | OK | Pass
E1030 | OK | OK | OK | OK | OK | Pass
E1031 | OK | OK | OK | OK | OK | Pass
E1032 | OK | OK | OK | OK | OK | Pass
E1033 | OK | OK | OK | OK | OK | Pass
E1034 | OK | Missing/invalid | OK | OK | OK | Fail
E1035 | OK | OK | OK | OK | OK | Pass
E1036 | OK | OK | OK | OK | OK | Pass
E1037 | OK | OK | OK | OK | OK | Pass
E1038 | OK | OK | OK | OK | OK | Pass
E1039 | OK | OK | OK | OK | OK | Pass
E1040 | OK | OK | OK | OK | OK | Pass
E1041 | OK | OK | OK | OK | OK | Pass
E1042 | OK | OK | Invalid code | OK | OK | Fail
E1043 | OK | OK | OK | OK | OK | Pass
E1044 | OK | OK | OK | OK | OK | Pass
E1045 | OK | OK | OK | OK | OK | Pass
E1046 | OK | OK | OK | OK | OK | Pass
E1047 | OK | OK | OK | OK | OK | Pass
E1048 | OK | OK | OK | OK | OK | Pass
E1049 | OK | OK | OK | OK | OK | Pass
E1050 | OK | OK | OK | OK | OK | Pass
E1051 | OK | OK | OK | Out of range | OK | Fail
E1052 | OK | OK | OK | OK | OK | Pass
E1053 | OK | OK | OK | OK | OK | Pass
E1054 | OK | OK | OK | OK | OK | Pass
E1055 | OK | OK | OK | OK | OK | Pass
E1056 | OK | OK | OK | OK | OK | Pass
E1057 | OK | OK | OK | OK | OK | Pass
E1058 | OK | OK | OK | OK | OK | Pass
E1059 | OK | OK | OK | OK | OK | Pass
E1060 | OK | OK | OK | OK | OK | Pass
E1007 | Duplicate | OK | OK | OK | OK | Fail
E1023 | Duplicate | OK | OK | OK | OK | Fail

## Recon
Recon - legacy vs new WFM field-level reconciliation
One row per legacy record. Lookups use INDEX/MATCH on Employee ID into WFM_Import.
Employee ID | Region (legacy) | In WFM? | Rate check | Award check | Region check | Start date check | Overall
E1001 | VIC | Yes | OK | OK | OK | OK | Match
E1002 | NSW | Yes | OK | OK | OK | OK | Match
E1003 | VIC | No | n/a | n/a | n/a | n/a | Missing
E1004 | VIC | Yes | OK | OK | OK | OK | Match
E1005 | NSW | Yes | OK | OK | OK | OK | Match
E1006 | NSW | Yes | Mismatch | OK | OK | OK | Mismatch
E1007 | VIC | Yes | OK | OK | OK | OK | Match
E1008 | VIC | Yes | OK | OK | OK | OK | Match
E1009 | VIC | Yes | OK | Mismatch | OK | OK | Mismatch
E1010 | QLD | Yes | OK | OK | OK | OK | Match
E1011 | NSW | Yes | OK | OK | OK | OK | Match
E1012 | NZ | Yes | Mismatch | OK | OK | OK | Mismatch
E1013 | NZ | Yes | OK | OK | OK | OK | Match
E1014 | VIC | Yes | OK | OK | OK | OK | Match
E1015 | QLD | Yes | OK | OK | OK | OK | Match
E1016 | NSW | No | n/a | n/a | n/a | n/a | Missing
E1017 | QLD | Yes | OK | OK | OK | OK | Match
E1018 | NSW | Yes | OK | OK | OK | OK | Match
E1019 | QLD | Yes | OK | OK | OK | OK | Match
E1020 | NZ | Yes | OK | Mismatch | OK | OK | Mismatch
E1021 | NZ | Yes | OK | OK | OK | OK | Match
E1022 | QLD | Yes | OK | OK | Mismatch | OK | Mismatch
E1023 | QLD | Yes | OK | OK | OK | OK | Match
E1024 | NZ | Yes | OK | OK | OK | OK | Match
E1025 | NSW | Yes | Mismatch | OK | OK | OK | Mismatch
E1026 | VIC | Yes | OK | OK | OK | OK | Match
E1027 | NZ | Yes | OK | OK | OK | OK | Match
E1028 | NZ | Yes | OK | OK | OK | OK | Match
E1029 | QLD | Yes | OK | OK | OK | OK | Match
E1030 | VIC | No | n/a | n/a | n/a | n/a | Missing
E1031 | NZ | Yes | OK | OK | OK | OK | Match
E1032 | NSW | Yes | OK | OK | OK | OK | Match
E1033 | QLD | Yes | OK | OK | OK | OK | Match
E1034 | NSW | Yes | OK | OK | OK | OK | Match
E1035 | NZ | Yes | OK | OK | OK | OK | Match
E1036 | NZ | Yes | OK | OK | OK | OK | Match
E1037 | NZ | Yes | OK | OK | OK | OK | Match
E1038 | NSW | Yes | Mismatch | OK | OK | OK | Mismatch
E1039 | QLD | Yes | OK | OK | OK | OK | Match
E1040 | NZ | Yes | OK | OK | OK | OK | Match
E1041 | QLD | Yes | OK | OK | OK | OK | Match
E1042 | NZ | Yes | OK | OK | OK | OK | Match
E1043 | NSW | Yes | OK | OK | OK | OK | Match
E1044 | VIC | Yes | OK | OK | OK | OK | Match
E1045 | QLD | Yes | OK | Mismatch | OK | OK | Mismatch
E1046 | QLD | Yes | OK | OK | OK | OK | Match
E1047 | QLD | Yes | OK | OK | OK | OK | Match
E1048 | VIC | Yes | OK | OK | OK | OK | Match
E1049 | VIC | No | n/a | n/a | n/a | n/a | Missing
E1050 | VIC | Yes | OK | OK | OK | OK | Match
E1051 | VIC | Yes | OK | OK | OK | OK | Match
E1052 | NSW | Yes | OK | OK | OK | OK | Match
E1053 | VIC | Yes | Mismatch | OK | OK | OK | Mismatch
E1054 | QLD | Yes | OK | OK | OK | OK | Match
E1055 | NZ | Yes | OK | OK | OK | OK | Match
E1056 | NSW | Yes | OK | OK | Mismatch | OK | Mismatch
E1057 | NSW | Yes | OK | OK | OK | OK | Match
E1058 | VIC | Yes | OK | OK | OK | OK | Match
E1059 | QLD | Yes | OK | OK | OK | OK | Match
E1060 | NZ | Yes | OK | OK | OK | OK | Match
E1007 | VIC | Yes | OK | OK | OK | OK | Match
E1023 | QLD | Yes | OK | OK | OK | OK | Match

## UAT
UAT - test cases and execution log
Execution results are SIMULATED for the portfolio. Change Status via dropdown; Dashboard updates.
Test ID | Req ID | Scenario | Steps | Expected result | Status | Defect ref
T01 | R01 | Mobile clock-in inside depot geofence | 1. Open app 2. Tap Clock In at depot | Clock-in recorded with GPS, status Active | Pass
T02 | R01 | Clock-in outside geofence | 1. Move 2km from depot 2. Tap Clock In | Warning shown, entry flagged for approval | Pass
T03 | R02 | Roster skills match | 1. Build roster for job needing licensed technician | Only qualified staff offered | Pass
T04 | R03 | Overtime beyond 7.6 hrs | 1. Submit 10.5 hr shift for FS-L2 | 2.9 OT hrs @1.5x (worked example on Config sheet) | Pass
T05 | R03 | Weekend penalty rate TL-L4 | 1. Submit Saturday shift for TL-L4 | Rate x1.75 applied | Fail | DEF-004
T06 | R04 | Leave request approval | 1. Employee requests 2 days 2. Leader approves | Balance reduced, roster updated | Pass
T07 | R05 | Dispatch nearest qualified crew | 1. Create urgent job in QLD | Nearest qualified crew suggested | Pass
T08 | R05 | Dispatch with no crew available | 1. Create job outside coverage | Escalation alert raised | Blocked | DEF-007
T09 | R06 | Migrated record count matches | 1. Compare Recon summary | 100% of legacy IDs in WFM | Fail | DEF-001
T10 | R06 | Rates and award codes match | 1. Review Recon mismatches | Zero field mismatches | Fail | DEF-002
T11 | R07 | Timesheet approval before cut-off | 1. Leader approves queue | Approved hours locked | Pass
T12 | R08 | Payroll export file format | 1. Run export 2. Validate against spec | File passes payroll validation | Pass
T13 | R09 | NZ public holiday pay | 1. Submit NZ shift on public holiday | NZ holiday rule applied | Not Run
T14 | R10 | Labour cost report totals | 1. Run weekly report 2. Compare to Excel | Totals agree to the cent | Pass
T15 | R11 | Employee cannot approve own timesheet | 1. Login as team leader 2. Approve own | Action blocked | Pass
T16 | R12 | Audit trail on edit | 1. Edit hours 2. Open audit log | Who/when/old/new value logged | Pass
T17 | R13 | Roster publish performance | 1. Publish 2,300-person roster | Completes < 60 seconds | Not Run

## GoLive_Training
GoLive_Training - cutover checklist and training materials plan
Cutover task | Owner | When | Status
Freeze legacy data changes | Payroll Manager | T-5 days | Done
Run final extract and Validation checks | BA | T-4 days | Done
Load to WFM and run Recon | BA / Vendor | T-3 days | In progress
Resolve Recon mismatches (zero critical) | BA / Vendor | T-2 days | Not started
Go/No-go meeting | Head of Transformation | T-1 day | Not started
Go live and hypercare begins | All | T-0 | Not started
Audience | Training material | Format | Req ID
Employee | Mobile clock-in/out quick card | 1-page PDF | R01
Team Leader | Approve timesheets and exceptions guide | 6-page guide | R07
Depot Admin | Rostering and leave user guide | 10-page guide | R02
Payroll | Award rules and export runbook | 8-page guide | R03
Trainers | Train-the-trainer deck and demo script | Slides | R14

## Resume_Uplift
Resume_Uplift - map each SkillSyncer gap to project evidence
Only use a bullet once you have actually built/done that part. Project is labelled self-directed, matching your existing resume style.
SkillSyncer gap keywords | Project evidence | Suggested resume bullet (edit to match what you did)
Data Migration, Migration, Reconciliation | WFM_Import + Recon sheets | Designed legacy-to-WFM data migration reconciliation across 60+ records, identifying 4 missing records, 5 rate and 3 award mismatches via INDEX/MATCH checks.
Data Validation, Pivot Tables, Reporting Requirements | Validation sheet + Dashboard summary tables | Built pre-migration validation rules (duplicates, invalid codes, out-of-range rates) and pivot-style summaries, giving a go/no-go view of data quality.
Requirements Gathering, System Requirements, Stakeholder Engagement | Requirements (RTM) | Documented 15 prioritised (MoSCoW) requirements across 11 stakeholder groups with traceability to test cases and coverage gap checks.
Process Mapping (current/future state) | Process_Map | Mapped current vs future state timesheet-to-pay process, linking 7 pain points to system requirements.
System Configuration, Support System | Config sheet | Defined award-based pay rule configuration (rates, overtime, weekend multipliers) and validated with a worked overtime test.
Testing, Performance Testing | UAT | Authored 17 UAT cases traced to requirements, logged defects and tracked pass rate (incl. performance test for 2,300 users).
Training Materials, System Implementation, Launch | GoLive_Training | Planned cutover checklist and role-based training materials for go-live and hypercare.
Agile / waterfall | Add yourself | Add a line on Agile ways of working from your Deakin work or internship (e.g. sprint-style backlog, stand-ups) only if true.
Communication, Confidence | Summary | Rework summary to lead with 'stakeholder communication' and system implementation.